## Sheet1
Website Re design
S.No | Activity | Tasks | Number of Days | Start Date | End Date | Resource/Team | Development Status | Project Status
1 | Home Page | Involved in bussiness meetings and gathered requirements from Bussiness | 5days | 2017-08-01 | 2017-08-07 | Natalie Tate | Completed | Completed
Started Creating Template for Home Pages
Developed Component's for Home pages
Developed Accesability Features
Fixed defects for the Home pages and sent for demo
2 | Banking Modules | Gathered requirements from Bussiness | 4days | 2017-08-08 | 2017-08-11 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Banking Pages
Developed Component's for Banking pages
Developed Accesability Features
Fixed defects for the Banking pages and sent for demo
3 | Loans | Gathered requirements from Bussiness | 3days | 2017-08-14 | 2017-08-16 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Loans Pages
Developed Component's for Loans pages
Developed Accesability Features
Fixed defects for the pages and sent for demo
4 | Home Loans & reality | Gathered requirements from Bussiness | 5days | 2017-08-17 | 2017-08-23 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Home loans and reality Pages
Developed Component's for Home loans and reality Pges
Developed Accesability Features
Fixed defects for the Home loans and reality Pages and sent for demo
5 | Bussiness | Gathered requirements from Bussiness | 4days | 2017-08-24 | 2017-08-29 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Bussiness Pages
Developed Component's for Bussiness pages
Developed Accesability Features
Fixed defects for the Bussiness page and sent for demo
6 | Educational Resources | Gathered requirements from Bussiness | 5days | 2017-08-30 | 2017-09-06 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Educational Resources Pages
Developed Component's for Educational Resources page
Developed Accesability Features
Fixed defects for the Educational Resources page and sent for demo
7 | Investments | Gathered requirements from Bussiness | 5days | 2017-09-07 | 2017-09-13 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Investments Page
Developed Component's for Investments page
Developed Accesability Features
Fixed defects for the Home page and sent for demo
8 | Insurance | Gathered requirements from Bussiness | 4days | 2017-09-14 | 2017-09-19 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Insurance Page
Developed Component's for Insurance page
Developed Accesability Features
Fixed defects for the Home page and sent for demo
9 | Educational Resources | Gathered requirements from Bussiness | 3days | 2017-09-20 | 2017-09-22 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Home Page
Developed Component's for Home page
Developed Accesability Features
Fixed defects for the Home page and sent for demo
10 | Investments | Gathered requirements from Bussiness | 5days | 2017-09-25 | 2017-09-29 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Home Page
Developed Component's for Home page
Developed Accesability Features
Fixed defects for the Home page and sent for demo
loan Status Re Design
11 | Loans Satus Menu page | Continued working Development on Loan status Re design Project | 5days | 2017-10-02 | 2017-10-06 | Paul Ripley | Completed | Pending
Removed old styling
Created new Template structure according to the new visual design
Developed the loan Menu page
Deployed Loan menu page for UAT
Fixed Bugs from UAT and sent for demo
12 | Loan status page | Started workong on Loan status page | 4days | 2017-10-10 | 2017-10-13 | Paul Ripley | Completed
Developed loan status page Action Items according to the design
Re-Organised the Properties of application
Added new data properties from Data base which are introduced in redesign
Deployed Loan Status page for UAT
Fixed Bugs from UAT and sent for demo
13 | Accepting and decling pages | Developed pages for accepting loan creiteria | 2days | 2017-10-16 | pending | Paul Ripley | Pending
Developed pages for declining loan Creiteria
Deployed in UAT environment for testing
Fixed Bugs from UAT and sent for demo
14 | Document Upload items | Started working On Document Upload Items | 2days | 2017-10-18 | pending | Paul Ripley | Pending
Developed Functionality for Uploading Documents
Developed Functionality for multiple Uploading Documents at one time
Adding a new Feature to remove and add a document Dynamically